## Project Status
PROJECT MANAGEMENT SYSTEM - MODULE STATUS TRACKER
S.No | Module | Sub-Module | Status | Progress % | Priority | Start Date | End Date | Estimated Completion | Notes
1 | Authentication & Authorization | User Login | Completed | 100 | High | 2024-01-01 | 2024-01-15 | 2024-01-01
2 | Authentication & Authorization | User Registration | Completed | 100 | High | 2024-01-01 | 2024-01-15 | 2024-01-01
3 | Authentication & Authorization | Password Reset | In Progress | 60 | High | 2024-01-16 | 2024-02-01 | 2024-01-22
4 | Authentication & Authorization | Roles & Permissions | In Progress | 70 | High | 2024-01-16 | 2024-02-15 | 2024-01-25
5 | Dashboard & Home | Dashboard Overview | In Progress | 50 | High | 2024-01-20 | 2024-02-20 | 2024-02-04
6 | Dashboard & Home | Widgets & Cards | Not Started | 0 | Medium | 2024-02-15 | 2024-03-01 | 2024-03-01
7 | Dashboard & Home | Analytics Integration | Not Started | 0 | Medium | 2024-03-01 | 2024-03-20 | 2024-03-20
8 | Projects Module | Project Listing | Completed | 100 | High | 2024-01-01 | 2024-01-10 | 2024-01-01
9 | Projects Module | Project Details | Completed | 100 | High | 2024-01-05 | 2024-01-15 | 2024-01-05
10 | Projects Module | Create/Edit Project | Completed | 100 | High | 2024-01-01 | 2024-01-12 | 2024-01-01
11 | Projects Module | Project Status Management | In Progress | 80 | High | 2024-01-15 | 2024-02-01 | 2024-01-18
12 | Tasks & Sprint Management | Task Creation & Assignment | In Progress | 70 | High | 2024-02-01 | 2024-02-20 | 2024-02-06
13 | Tasks & Sprint Management | Task Status Tracking | In Progress | 65 | High | 2024-02-05 | 2024-02-25 | 2024-02-12
14 | Tasks & Sprint Management | Sprint Planning | Not Started | 0 | Medium | 2024-02-20 | 2024-03-10 | 2024-03-10
15 | Tasks & Sprint Management | Sprint Execution | Not Started | 0 | Medium | 2024-03-01 | 2024-03-20 | 2024-03-20
16 | Client Management | Client Listing | Completed | 100 | High | 2024-01-01 | 2024-01-10 | 2024-01-01
17 | Client Management | Client Details | Completed | 100 | High | 2024-01-05 | 2024-01-15 | 2024-01-05
18 | Client Management | Client Profile Management | In Progress | 60 | Medium | 2024-02-01 | 2024-02-25 | 2024-02-10
19 | Lead & Deal Management | Lead Management | Not Started | 0 | Medium | 2024-03-01 | 2024-03-25 | 2024-03-25
20 | Lead & Deal Management | Lead Conversion | Not Started | 0 | Medium | 2024-03-25 | 2024-04-10 | 2024-04-10
21 | Lead & Deal Management | Deal Pipeline | Not Started | 0 | Medium | 2024-03-15 | 2024-04-05 | 2024-04-05
22 | Lead & Deal Management | Deal Tracking | Not Started | 0 | Medium | 2024-04-01 | 2024-04-20 | 2024-04-20
23 | Employee Management | Employee Listing | In Progress | 60 | High | 2024-02-01 | 2024-02-20 | 2024-02-08
24 | Employee Management | Employee Profile | In Progress | 50 | High | 2024-02-10 | 2024-03-01 | 2024-02-20
25 | Employee Management | Timesheet Management | Not Started | 0 | Medium | 2024-03-10 | 2024-03-30 | 2024-03-30
26 | Employee Management | Attendance Tracking | Not Started | 0 | Low | 2024-03-20 | 2024-04-10 | 2024-04-10
27 | Finance & Invoicing | Invoice Generation | Not Started | 0 | Medium | 2024-04-01 | 2024-04-25 | 2024-04-25
28 | Finance & Invoicing | Payment Tracking | Not Started | 0 | Medium | 2024-04-10 | 2024-05-01 | 2024-05-01
29 | Finance & Invoicing | Financial Reports | Not Started | 0 | Low | 2024-04-20 | 2024-05-15 | 2024-05-15
30 | Communication | Announcements | In Progress | 40 | Medium | 2024-02-01 | 2024-02-25 | 2024-02-15
31 | Communication | Notifications | In Progress | 55 | Medium | 2024-02-10 | 2024-03-05 | 2024-02-20
32 | Communication | Meeting Schedule | Not Started | 0 | Low | 2024-03-15 | 2024-04-05 | 2024-04-05
33 | Reporting & Analytics | Project Reports | Not Started | 0 | Medium | 2024-04-01 | 2024-04-20 | 2024-04-20
34 | Reporting & Analytics | Team Performance Reports | Not Started | 0 | Low | 2024-04-15 | 2024-05-01 | 2024-05-01
35 | Reporting & Analytics | Custom Reports Builder | Not Started | 0 | Low | 2024-05-01 | 2024-05-30 | 2024-05-30
36 | Settings & Configuration | Company Settings | Completed | 100 | High | 2024-01-01 | 2024-01-10 | 2024-01-01
37 | Settings & Configuration | Application Settings | In Progress | 70 | Medium | 2024-02-01 | 2024-02-20 | 2024-02-06
38 | Settings & Configuration | User Preferences | Not Started | 0 | Low | 2024-03-01 | 2024-03-20 | 2024-03-20
39 | Documentation | API Documentation | In Progress | 50 | Medium | 2024-02-01 | 2024-02-28 | 2024-02-14
40 | Documentation | User Guide | Not Started | 0 | Low | 2024-04-01 | 2024-04-30 | 2024-04-30
41 | Documentation | Developer Documentation | Not Started | 0 | Low | 2024-03-15 | 2024-04-15 | 2024-04-15

## Summary
PROJECT PROGRESS SUMMARY
Metric | Count | Percentage
Total Modules | 12 | 100%
Total Sub-Modules | 41 | 100%
Completed Sub-Modules | 8 | 19.5%
In Progress Sub-Modules | 13 | 31.7%
Not Started Sub-Modules | 20 | 48.8%
OVERALL PROJECT PROGRESS | 19.5%

## Module Progress
MODULE-WISE PROGRESS BREAKDOWN
Module | Total Sub-Modules | Completed | In Progress | Not Started | Overall Progress %
Authentication & Authorization | 4 | 2 | 2 | 0 | 50.0%
Dashboard & Home | 3 | 0 | 1 | 2 | 0.0%
Projects Module | 4 | 3 | 1 | 0 | 75.0%
Tasks & Sprint Management | 4 | 0 | 2 | 2 | 0.0%
Client Management | 3 | 2 | 1 | 0 | 66.7%
Lead & Deal Management | 4 | 0 | 0 | 4 | 0.0%
Employee Management | 4 | 0 | 2 | 2 | 0.0%
Finance & Invoicing | 3 | 0 | 0 | 3 | 0.0%
Communication | 3 | 0 | 2 | 1 | 0.0%
Reporting & Analytics | 3 | 0 | 0 | 3 | 0.0%
Settings & Configuration | 3 | 1 | 1 | 1 | 33.3%
Documentation | 3 | 0 | 1 | 2 | 0.0%